## Sheet1
Phases | Start Date | Days to Complete
Project Planning | 2024-01-05 | 10
Research and Analysis | 2024-01-15 | 12
User Interface (UI) Design | 2024-01-27 | 15
Database Design and Setup | 2024-02-11 | 7
Backend Development | 2024-02-18 | 12
Frontend Development | 2024-03-03 | 15
Testing | 2024-03-18 | 4
Deployment | 2024-03-22 | 5
Training and Documentation | 2024-03-27 | 10
Post-Implementation Review | 2024-04-06 | 3
Project Closure | 2024-04-09 | 3